## Bugs & Changes & Report
Date | Received Bugs and changes | Soved / Pending | Solved Date | Solved time | comments
2023-05-12 | In mobile menu under the join us tab the job opening has to be in carousel. | Solved
| In the mobile screen under the job carousel green arroe has to be visible. | Solved
| In the footer tab, Follow us tab to placed in center in the mobile screens. | solved
| In the footer tab, Select region when clicked is reloading the page. | solved
| In the footer tab, Select Region the list of countries has to be added. | solved
| Top of the page (in banner) if we swipe left, the page will move and right side will be white/blank | Pending |  |  | Need more time to figure out what is casing the issue.
| Make all text (logo, menu list, social logo-linkedin) in same left alignment.. And keep all in middle of the popup... | Solved
| In contact page footer, something like a vibration in texts... Open in your mobile and go to contact page footer... Questions area and below... Then return to top slowly.... | Pending |  |  | The framer motion animation is causing this issue. Since I am new to this library need some more time to fix this bug. To make the animation smoothly disapper and apear.
2023-05-12 | Previous Pending bugs which resolved
22:47 | Top of the page (in banner) if we swipe left, the page will move and right side will be white/blank | Solved | 2023-05-12 | 22:53
| In contact page footer, something like a vibration in texts... Open in your mobile and go to contact page footer... Questions area and below... Then return to top slowly.... | Solved | 2023-05-12 | 22:53
Report
Resolved the Above mentioned bugs
Successfully created the About Us page
Date | Received Bugs and changes | Soved / Pending | Solved Date | Solved time | comments
2023-05-13 | Initially minimum text will be visible but when clicked in the more button all the text gets visible under the About Mcabee in who we are page. | Solved | 2023-05-13 | 22:30
Report
Resolved the Above mentioned bug
Started and completed the services page.
Date | Received Works | Soved / Pending | Solved Date | Solved time | comments
2023-05-15 | Received the design for Contact Page, | Pending
| Received the design for Carrers page. | Pending
| Received the design for Carrers Apply page. | Pending
| Received the design for Products page. | Pending
| Received the design for Signle Product page. | Pending
Report
2023-05-15 | Created the components and layouts for the above mentioned pages except the Contact Page. I have today prepared the layout and statuc design of the above mentioned pages and tomorrow (16-05-2023) I will be writing the functions to dynamically render the data into the completed designs.
Also at the Carrers and carrer apply page have to write the functions for uploading the resume PDF document and user details and also to send that details to the email.
Have to code the 2nd layout design for the contact page which will happen tomorrow if possible.
Date | Received Works | Soved / Pending | Solved Date | Solved time | comments
2023-05-19 | Header menu change | Solved | 2023-05-19 | 16:51
| Search box in header Section 2 | Solved | 2023-05-19 | 17:08
| File upload and submit button design In carrers page | Solved | 2023-05-19 | 17:08
| File upload and submit button design In carrersApply page | Solved | 2023-05-19 | 21:41
| Space between social media icons in footer | Solved | 2023-05-19 | 17:13
| 4 links align to left and give more space from headline and paragraph | Solved | 2023-05-19 | 17:36
| In mobile make it all centre align the services in home page | Solved | 2023-05-19 | 17:40
| Bootstrap carousel not working. | Solved | 2023-05-19 | 18:30
Report
2023-05-19 | Today completed the above changes
Completed the functions to send emails when the user uploads files and data.
Date | Received Works | Soved / Pending | Solved Date | Solved time | comments
2023-05-22 | Product Carousel in home page make the width above container in responsive | Solved | 2023-05-22 | 11:47
| News box in responsive page width 100% | Solved | 2023-05-22 | 11:47
| I avoid this type search bar and give u the new one, without the product selection dropdown... In last figma file | Solved | 2023-05-22 | 12:13 | Only search or only select dropdown
| Size of available notice in home page make as same as in size of in product page | Solved | 2023-05-22 | 13:03
| When i click the arrow button from index banner, it will redirect to this page.. Its heading is Services... But no services listed here... | Solved | 2023-05-22 | 13:07 | Index banner link should goes to service page…
| Career CV upload option.... | Solved | 2023-05-22 | 13:13
| See the search box width... I said keep all search box in same size... Keep all buttons in same size... Every page, different size.... How??? | Solved | 2023-05-22
| This is my figma design file.. See the spacing between each services | Solved | 2023-05-22 | 13:27